## Task_Table
ID | Active | Task Mode | Name | Duration | Start | Finish | Predecessors | Outline Level | Notes
1 | Yes | Auto Scheduled | Phase A | 63 days | August 14, 2013 8:00 AM | November 8, 2013 5:00 PM |  | 1
2 | Yes | Manually Scheduled | SRS - Initial Draft | 63 days | August 14, 2013 8:00 AM | November 8, 2013 5:00 PM |  | 2
3 | Yes | Manually Scheduled | SPMP - Initial Draft | 63 days | August 14, 2013 8:00 AM | November 8, 2013 5:00 PM |  | 2
4 | Yes | Auto Scheduled | Phase B | 8 days | November 11, 2013 8:00 AM | November 20, 2013 5:00 PM | 1 | 1
5 | Yes | Auto Scheduled | "Project Requirements" Presentation | 8 days | November 11, 2013 8:00 AM | November 20, 2013 5:00 PM | 1 | 2
6 | Yes | Manually Scheduled | "Project Requirements" Presentation - Initial Draft | 3 days | November 11, 2013 8:00 AM | November 13, 2013 5:00 PM | 1 | 3
7 | Yes | Manually Scheduled | "Project Requirements" Presentation - Final Draft | 4 days | November 14, 2013 8:00 AM | November 19, 2013 5:00 PM | 6 | 3
8 | Yes | Manually Scheduled | "Project Requirements" Presentation - Presentation | 1 day | November 20, 2013 8:00 AM | November 20, 2013 5:00 PM | 7 | 3
9 | Yes | Auto Scheduled | Phase C | 109 days | November 21, 2013 8:00 AM | April 22, 2014 5:00 PM | 4 | 1
10 | Yes | Auto Scheduled | PlasmaGraph | 86 days | November 21, 2013 8:00 AM | March 20, 2014 5:00 PM | 4 | 2
11 | Yes | Manually Scheduled | PlasmaGraph - Data-Reading Module | 86 days | November 21, 2013 8:00 AM | March 20, 2014 5:00 PM | 4 | 3
12 | Yes | Manually Scheduled | PlasmaGraph - Data-Graphing Module | 86 days | November 21, 2013 8:00 AM | March 20, 2014 5:00 PM | 4 | 3
13 | Yes | Manually Scheduled | PlasmaGraph - Program Graphical User Interface | 63 days | November 21, 2013 8:00 AM | February 17, 2014 5:00 PM | 4 | 3
14 | Yes | Manually Scheduled | SDD - Initial Draft | 28 days | November 21, 2013 8:00 AM | December 30, 2013 5:00 PM | 4 | 2
15 | Yes | Manually Scheduled | STD - Initial Draft | 109 days | November 21, 2013 8:00 AM | April 22, 2014 5:00 PM | 4 | 2
16 | Yes | Manually Scheduled | Code Documentation - Initial Draft | 86 days | November 21, 2013 8:00 AM | March 20, 2014 5:00 PM | 4 | 2
17 | Yes | Auto Scheduled | Phase D | 27 days | April 23, 2014 8:00 AM | May 29, 2014 5:00 PM | 9 | 1
18 | Yes | Auto Scheduled | User Manual and Installation Guide | 22 days | April 23, 2014 8:00 AM | May 22, 2014 5:00 PM | 9 | 2
19 | Yes | Manually Scheduled | User Manual and Installation Guide - Initial Draft | 6 days | April 23, 2014 8:00 AM | April 30, 2014 5:00 PM | 9 | 3
20 | Yes | Manually Scheduled | User Manual and Installation Guide - Final Draft | 16 days | May 1, 2014 8:00 AM | May 22, 2014 5:00 PM | 19 | 3
21 | Yes | Manually Scheduled | SRS - Final Draft | 16 days | April 23, 2014 8:00 AM | May 14, 2014 5:00 PM | 9 | 2
22 | Yes | Manually Scheduled | SDD - Final Draft | 27 days | April 23, 2014 8:00 AM | May 29, 2014 5:00 PM | 9 | 2
23 | Yes | Manually Scheduled | STD - Final Draft | 27 days | April 23, 2014 8:00 AM | May 29, 2014 5:00 PM | 9 | 2
24 | Yes | Auto Scheduled | STD - User Tests | 1 day | May 16, 2014 8:00 AM | May 16, 2014 5:00 PM | 9 | 3
25 | Yes | Manually Scheduled | SPMP - Final Draft | 22 days | April 23, 2014 8:00 AM | May 22, 2014 5:00 PM | 9 | 2
26 | Yes | Manually Scheduled | Code Documentation - Final Draft | 24 days | April 23, 2014 8:00 AM | May 26, 2014 5:00 PM | 9 | 2
27 | Yes | Manually Scheduled | Phase E | 28 days | April 23, 2014 8:00 AM | May 30, 2014 5:00 PM | 17 | 1
28 | Yes | Manually Scheduled | "Using PlasmaGraph" Presentation | 28 days | April 23, 2014 8:00 AM | May 30, 2014 5:00 PM | 17 | 2
29 | Yes | Manually Scheduled | "Using PlasmaGraph" Presentation - Initial Draft | 1 day | May 1, 2014 8:00 AM | May 1, 2014 5:00 PM | 19 | 3
30 | Yes | Manually Scheduled | "Using PlasmaGraph" Presentation - Final Draft | 2 days | May 20, 2014 8:00 AM | May 21, 2014 5:00 PM | 29 | 3
31 | Yes | Manually Scheduled | "Using PlasmaGraph" Presentation - Presentation | 1 day | May 30, 2014 8:00 AM | May 30, 2014 5:00 PM | 30 | 3
32 | Yes | Manually Scheduled | Final Project Presentation | 28 days | April 23, 2014 8:00 AM | May 30, 2014 5:00 PM | 17 | 2
33 | Yes | Manually Scheduled | Final Project Presentation - Initial Draft | 1 day | May 1, 2014 8:00 AM | May 1, 2014 5:00 PM | 19 | 3
34 | Yes | Manually Scheduled | Final Project Presentation - Final Draft | 2 days | May 20, 2014 8:00 AM | May 21, 2014 5:00 PM | 33 | 3
35 | Yes | Manually Scheduled | Final Project Presentation - Presentation | 1 day | May 30, 2014 8:00 AM | May 30, 2014 5:00 PM | 34 | 3

## Resource_Table
ID | Name | Initials | Type | Material Label | Group | Email Address | User Logon Account | Max Units | Standard Rate | Cost Per Use | Notes

## Assignment_Table
Task Name | Resource Name | % Work Complete | Work | Units